

Meeting




of the

District officers




held on




18.07.09

  Special Secretary cum Director General School Education  &

     State Project Director Sarva Shiksha Abhiyan Authority, Punjab
Minutes of the Monthly meeting held on 18.07. 2009 to review 
the Mid Day  Meal scheme in the State of Punjab
1.0 
A   meeting  was  held  in  the   office  of  Director  General  School Education, Government of Punjab, on 18.07.2009 at SCO No 104-106, Sector 34-A, Chandigarh to review the implementation of the Mid Day Meal scheme in the State of Punjab. Mr. Krishan Kumar, Director General School Education chaired the meeting.
2.0 
List of officers who attended the meeting is enclosed at Annexure  'A'.

3.0 
After review of action taken following decisions were taken in the meeting:-
3.2 
Lifting and utilization of foodgrains for April to June, 2009
(i) 

It was noted that 1840.24 MT of rice and 1806.61 MT of wheat is available  as  on 01.07.2009  in  all  the  districts  to  run the Mid Day Meal scheme during the coming months in primary schools. All DEOs  were asked to inform immediately in case there is any shortage of foodgrains in their  districts.  Manager   Foodgrains  informed  that  districts  of   Amritsar, Barnala, Fatehgarh Sahib, Gurdaspur ,Jalandhar, Ludhiana, Patiala , SAS Nagar  and  Tarn Taran  did not lift full qty. of foodgrains allocated in pursuance of the orders passed by Government of India allocating foodgrains for the first quarter. 


On the request  of DEO  Tarn Taran , 166 MT  of foodgrains  allocated  to   Faridkot  was  got  diverted  to Tarn Taran. But , it was not lifted  by   Tarn Taran   District Education Officer, Tarn Taran   should  explain the reason for the same.
(iii) 
lt was also noted that quality of foodgrains is not checked at the source point as well as the destination point. As per Government of India guidelines, the DCs are the appropriate authority who are responsible to ensure that only Fair Average Quality (FAQ) foodgrain is lifted from FCI godown. All DCs may be requested again to ensure the compliance of  guidelines issued by Government of India asking them further to depute some senior officer of the rank of Assistant Commissioner for this purpose under intimation to this office.;
(v) 
On lifting of the foodgrains for the Upper Primary sections, it
was noted that 2850.68 MT of Rice and 2371.96 MT of Wheat  stock is in hand of all districts to run Mid Day Meal scheme for Upper Primary sections. All DEOs confirmed that Mid Day Meal has been implemented in all the Upper Primary Schools in their respective districts. However, it was noted that despite having released the funds for the Upper Primary sections to the districts, the same have not reached to the schools till date. All DEOs (EE) were advised to get in touch with their DEOs (SE) and resolve all the pending issues.
 3.3 
Utilization of Cooking Cost:

(i) 
It was informed in the meeting that the funds have already been transferred electronically to the districts, to implement the Mid Day Meal scheme in the schools. All DEOs were advised to ensure that the funds reach the school without any delay. It was also decided that GM (MDM) in the head office may randomly enquire from schools on telephone whether they have funds or not;
(ii)
 It was noted that some funds are lying in excess in some of the schools / blocks whereas some of the schools are not having funds. This is primarily because of lack of adequate information with the DEOs. It was decided that cooking cost on monthly basis may be calculated in respect of each and every school and the same information be provided to DEOs by head office. This will perhaps ensure the proper utilization of funds. Similar information may also be prepared for the requirement of the foodgrains i.e. wheat and rice as well. Manager  foodgrains  informed , that   this  information  has been   prepared  in respect   of each   district   and  booklets  are  being  issued  to all  the  District  Education  Officers.  
3.4
 Utilization of Cooking Cost vis-à-vis Utilization of 
foodgrains.

(i) 
The information given by the districts was noted to be satisfactory. It was further noted that the DEOs may verify these figures once again.
3.5. 
Progress of Kitchen Sheds

(i) 
It was noted that out of 4571 kitchen sheds, only 4570 kitchen sheds have been constructed till date leaving a balance of 1 kitchen shed in the  district Tarn Taran , District Education  Officer was  asked  to explain  reason  for  the same. The progress  of construction  of  Kitchen Sheds  allotted  during  the  year 2008-09  was   found to   be  unsatisfactory  District education  officers  of the  districts where  work  has not  started  on  the  Kitchen  Sheds  were   advised  to attend   a meeting  at   Head Office  on 31.07.09   and  bring  the  latest  position   of the  construction  of Kitchen Sheds. Explanation  of District  Education  Officer, Ludhiana  may  be  called  for  not  starting  the  work   on   any   Kitchen Shed.

3.6 
Procurement of Kitchen devices through PUNSUP

(i) 
It  was  noted  that  out   of   4748  gas  connections,  only    4744 connections have been provided in the schools, leaving a balance of 4 connections in the  Bathinda district  District  Education  Officer (EE) , Bathinda explained that they were  short of funds due to revision of prices. Director  general  School Education reconciled that  a sum of  Rs.  6000   be give  to Bathinda  District  to   get the  connections  released. where 46 and 44 connections are pending. DEOs of these districts were advised to pursue this matter and achieve the target.
3.7
 Kitchen devices to be procured by D.C.

(i) 
It was noted that adequate funds have already been released to the D.C.s to procure Gas Bhattis, Fire Extinguishers and Gas connections. However,  as  on  30.06.2009,  Gas Bhattis,  Fire Extinguishers  and  Gas connections are still required to be procured in the district. Gurdaspur and Jalandhar. DEO Gurdaspur was advised to complete the task of obtaining  gas Connections on priority. However, it was decided that funds for 83  Gas connections  may be  released  to  Gurdaspur  district  as   these   have  fallen  short due to   revision  of prices.
3.8 
Storage Bins


It has been decided to procure Storage Bins in the schools out of the sale proceed of Bardana. Instructions and specification of the Storage Bins, capacity required and committee authoring to make the purchase is being sent separately.

3.9 
 Disposal of Used Bardana

 It was noted during previous meeting with great concern that the used Bardana is not being disposed of by the districts in a time bound manner. Moreover the used Bardana is not being accounted correctly. It was therefore decided previously that Manager Foodgrains may clearly calculate the quantity of the used Bardana in respect of each and every district on the basis of the utilization of the food grains during the previous years, the quantity of Bardana disposed of by the districts the balance Bardana so calculated may be compared with the Bardana which is physically present in the districts. For the purpose DEOs have been allotted dates in the month of June for the reconciliation of Bardana. Manager (Foodgrains) was requested to reconcile the figures at  least after 01.04.2008 and submit a report. However,  Manager  Foodgrains  informed  that  Bardana  Account  has been  reconciled and  report has been  submitted.  
4.0 
Health Check Up

(i) 
District of Ludhiana have not sent the health check up reports during the month of April and May 2009. It was decided that a reference may be made to Secretary Health requesting to direct the Civil Surgeons of these districts to send the reports to this office;

(ii)
 It was informed in the meeting that detailed discussions were held with Secretary Health in the meeting held on 10.06.2009. Certain information is required by the Department of Health from the Department of Schools as per the details given below (separate minutes have also been sent to the DEOs in this regard):

a. 
Health registers are to be maintained in all the schools;

b.
 The Nodal Officer be identified and nominated by the Department of School Education for each school for health check up;
c. 
Health cards are to be maintained in all the schools and certain information needs to be filled up and maintained by the school teachers themselves;

d. 
A certificate need to be given by the school teacher certifying whether the medical officers has visited in the school and have conducted the health check up or not;

e. 
The DEO shall provide a list of schools which was not visited by the health officers up to 30.06.2009 during the current financial year so that the same can be forwarded to the Department of Health for taking further necessary action. In the meeting of Health officers District Health Officers have informed that the list of schools provided by the D.E.Os is not correct and needs to be revised. 

 It was further advised by the Mission Director that D.E.Os should also be invited in the monthly meeting of the Health Staff, so that matters concerning both the Departments regarding school Health are discussed and resolved/ finalised.
4.1 
Minutes of the meeting of the District Level Steering and  Monitoring Committee
(i) 
It was noted that the all the districts except Patiala, Kapurthala, Bathinda, TarnTaran, Ferozepur and Nawanshaher held the monthly meeting to implement the scheme at district level during May, 2009. It was decided that a reference may be made to the DCs to hold this meeting regularly with a copy to Chief Secretary.
4.2 
Utilization Certificates
(i)
 It was noted that utilization certificates of the cooking cost for the primary schools has been received for the year 2007-08 from all the districts. However the utilization certificates of the cooking cost (Primary Classes I – V) for the funds released during the year 2008-09 are still pending from the districts as per the details given below:
(Rs. In Lacs)
	S.

No.
	District
	Amount released during the Year 2008-09

(Rs.)
	U.Cs being sent now for the amount

(Rs.)


	U.Cs already sent vide letter No. MDMC/MFA/2009/1759 dated 12/02/09 and MDMC/MFA/2009/3430 dated 11/05/09
	Pending  UC 



	1.
	Amritsar
	8,14,42,000
	74,00,000
	5,71,42,000
	1,69,00,000

	2.
	Barnala
	2,27,89,000
	15,00,000
	1,09,85,000
	1,03,04,000

	3.
	Bathinda
	4,28,85,000
	-
	2,30,60,903
	1,98,24,097

	4.
	Faridkot
	2,59,58,000
	-
	1,26,61,140
	1,32,96,860

	5.
	Fatehgarh Sahib
	3,09,00,000
	50,00,000
	2,59,00,000
	-

	6.
	Ferozepur
	7,25,90,000
	3,83,14,255
	1,60,00,000
	1,81,85,745

	7.
	Gurdaspur
	7,40,74,000
	-
	5,25,60,000
	2,15,14,000

	8.
	Hoshiarpur
	7,03,98,000
	1,00,16,966
	3,32,51,256
	2,71,29,778

	9.
	Jalandhar
	7,51,65,000
	-
	3,67,10,000
	3,84,55,000

	10.
	Kapurthala
	3,38,17,000
	-
	2,77,02,677
	61,14,323

	11.
	Ludhiana
	8,76,21,000
	3,64,15,000
	2,16,09,000
	2,95,97,000

	12.
	Mansa
	2,30,06,000
	26,75,948
	1,09,03,324
	94,26,728

	13.
	Moga
	5,84,51,000
	-
	2,68,51,000
	3,16,00,000

	14.
	Muktsar
	2,89,14,000
	34,06,234
	2,17,09,697
	38,00,069

	15.
	Nawanshaher
	2,71,41,500
	22,21,088
	1,91,40,327
	57,80,085

	16.
	Patiala
	6,61,98,000
	1,72,00,000
	2,78,98,000
	2,11,00,000

	17.
	Ropar
	3,11,95,000
	67,38,183
	1,64,95,000
	79,61,817

	18.
	Sangrur
	5,61,27,000
	82,21,280
	3,57,32,606
	1,21,73,114

	19.
	SAS Nagar
	2,77,08,000
	12,11,820
	1,35,15,796
	1,29,80,384

	20.
	Tarn Taran
	4,11,63,500
	30,00,000
	1,34,63,500
	2,47,00,000

	
	Total
	97,75,43,000
	14,33,20,774
	50,33,79,226
	33,08,43,000



All DEOs were advised to expedite the utilization certificates of the pending amount without any further delay. A reference may also be made to all  the DCs  in this regard. Further, utilization certificates of the cooking cost for the upper primary schools are also pending.
4.3 
Miscellaneous Issues:-

(i) 
It was noted that mid day meal is being provided in the districts of Ferozepur, Tarn Taran and Nawanshaher through Voluntary Agencies. Before starting the scheme from 15.09.2008 in the revised mode, some funds and the foodgrains must be lying in the schools. However, no action seems to have been taken by DEOs Ferozepur, Tarn Tarn and Nawanshaher. DEOs were advised once again to take the necessary action under intimation to the head office without any delay failing which the responsibility shall be fixed in case of any embezzlement either of funds or foodgrains comes to the notice of this office.

(ii) 
It was decided that a reference may be made all DEOs (SE) to send the U.C.s to DEOs (EE) who will further send it to Head Office.

Special Secretary cum Director

General School Education &

SPD SSA, Punjab

Encls: As above

