[image: image6.jpg]




[image: image7.jpg]



Tender Sr. No:……………………………………
REQUEST FOR PROPOSAL
For
Supply, Installation, Commissioning & Operationalization
of
Satellite Based (Ku-Band)
Receive Only Terminals (ROTs) Network
For
The EDUSAT Project

Government of Punjab
Through
Project Director, Punjab Edusat Society
SCO.104-106, 2nd Floor, Sector-34, Chandigarh

	1
	Tender No.
	

	2
	Total pages
	1 to 35

	3
	Description
	For Supply, Installation, Commissioning and Operationalization of Satellite Based Receive Only Terminals (ROTs) Network for the Edusat Project of the Govt of Punjab 

	4
	EMD
	Rs. 60,00,000/- (Rupees Sixty Lac only)

	5
	Last Date of Submission
	20th Sep. 2011 upto 2:30PM

	6
	Date of Opening of bid
	20th Sep. 2011 at 3:00PM


Table of Contents
	Sr. No
	Description
	Page No

	1
	Section-I
	

	
	Invitation for Bids
	

	2
	Section-II
	

	
	Scope of Work
	

	
	Introduction
	

	
	General Instruction
	

	3
	Section-III
	

	
	Installation of ROTs
	

	
	Site Survey
	

	
	Foundation
	

	
	Transportation
	

	
	Acceptance Test
	

	
	Maintenance Service
	

	
	Preventative Maintenance 
	

	
	LD Clause
	

	
	Operation Training
	

	
	Augmentation of the Network
	

	
	Other Terms & Conditions
	

	4
	Section-IV
	

	
	Bidders Qualifications
	

	5
	Section-V
	

	
	Submission of Bids
	

	6
	Section - VI
	

	
	Terms & Conditions of the Tender
	

	
	Payment Terms
	

	
	Performance Bank Guarantee (PBG)
	

	
	Time Schedule
	

	
	Warranty
	

	
	Penalty Clause for Late Delivery/Installation
	

	
	Force Majeure 
	

	
	Standard of Performance
	

	
	CAMC
	

	
	Other Terms & Conditions
	

	
	Arbitration 
	

	
	Jurisdiction
	

	7
	Annexure –I
	

	8
	Annexure-II
	

	9
	Annexure-III
	

	10
	Appendix 
	


Section – I

1.0 Invitation for Bids: 
1.1 This invitation of bid is for supply, installation, commissioning and Operationalization of Satellite Based Receive Only Terminals (ROTs) Network for the EDUSAT Project of the Government of Punjab.

1.2 Bidders are advised to study the Tender Document carefully. Submission of Tender shall be deemed to have been done after careful study and examination of the Tender Document with full understanding of its implications. 

1.3 Sealed offers should be submitted to Project Director Punjab Edusat Society, SCO.104-106 2nd floor, Sector-34 A Chandigarh not later than the last date and time of submission. 

1.4 All bids must be accompanied by an Earnest Money of Rs. 60 lacs (Rs Sixty lac only) in the form of Bank Draft, in favour of The Project Director cum Director General School Education, Punjab Edusat Society Payable at Chandigarh. 

1.5 This Tender document is not transferable 

1.6 Schedule for Invitation to Tender 

1.6.1 Time and date for receipt of Tender: 2.30 PM on 20.09.2011 

1.6.2
Date,  Time  &  Place  of  opening  of  bids:  3.00  PM  on  20.09.2011  in the office of the Project Director Punjab Edusat Society, Chandigarh, SCO.104-106, 2nd Floor, Sector-34 Chandigarh. 

1.7
Validity of the bid: 90 days from the date of opening of tenders.

1.8
Schedule for delivery: Delivery, commissioning and integration of equipment within 120 days of issue of LOI/order. 
1.9
The work can be split between more than one bidders. In such a case, (based on the lowest quoted rates) the Bid Evaluation Committee will decide a benchmark Price and the short listed bidders will have to match the so decided benchmark price. However, L1 will be given atleast 50% or more depended from his capacity to execute the order within the specified limit and the others the balance proportionately depending upon their capacity to execute the order within the specified time. 

1.10
The Punjab Edusat Society reserves the right to reject any or all tenders without assigning any reason. 
Note:

The PUNJAB EDUSAT SOCIETY shall not be responsible for any postal delay about non-receipt/non delivery of the documents.
Section – II
2.0 Scope of Work
2.1
Introduction  
2.1.1
Punjab Edusat Network is presently operational in Ku-Band channel # 4 of INSAT-4CR satellite. 

2.1.2
The Government of Punjab has embarked upon an ambitious programme for delivering quality education to the students of the educational institutions in the state of Punjab through INSAT-4CR. For delivering educational content, lectures are required to be broadcast/ recorded from studios based at Mohali. The state Government through the Punjab Education Society (PES) intends to select reputed companies/firms, with relevant experience to supply, install, commission and `Operationalization of Satellite Based Receive Only Terminals (ROTs).

2.1.3 This contract document gives the specifications, terms and conditions and other requirements of the system to be supplied by the vendor on turnkey basis. While the detailed specifications of all individual subsystems are given in Annexure-I. The format in which the commercial bid is to be submitted by the Bidder is given in Annexure-II. The list of deliverables is given in Annexure-III. 

2.1.4 At present PES is intending to procure 2790 Nos. of ROTs in initial phase. However the exact quantity may be decided at the time of placing purchase order. Vendor may submit their quote in slabs as per format given in Annexure-II. 

2.2 General Instructions:- 

2.2.1 It is mandatory for Bidder to submit the compliance of each and every part of this RFP (including general instructions, terms & conditions, schedule, maintenance, specifications of each system given in Annexure, etc.) in his technical bid failing which the proposal will not be evaluated and will be rejected without any further notice/communication to the bidder. 

2.2.2 This is a two part bid and Bidder, therefore, shall submit separate technical and commercial bids in two different envelopes.  The quote shall be inclusive of all the costs up to FOR destination, i.e. respective sites/locations in State of Punjab. However, price break viz. cost of material, customs duty, customs clearance charges (for import items) transportation, installation and commissioning, sales/service taxes in detailed price bid. The compliance statement, however, should be submitted along with the technical bid. 
2.2.3 The ROTs are required to be installed & commissioned at different locations in Punjab state. The list of locations and respective custodian at the site will be provided by Punjab Edusat Society later. 

2.2.4 RFP shall be treated by the successful Bidder as a ‘rate-contract’. Bidder shall provide the quote for different quantity slab as per Annexure-II , for all the items mentioned under “List of Deliverables” section of this RFP. The prices quoted by the vendor shall be valid for one year during which PUNJAB EDUSAT SOCIETY may place the order multiple times for different quantities, depending on requirement. The Rate contract can be extended for further period of one more year, if performance is satisfactory during first year.
2.2.5 The successful bidder (vendor) should stock required spares for ROT during warranty period to meet the uptime requirement. 

2.2.6 Generally, the Rate contract will be entered into on FIRM & FIXED price only. 

2.2.7 Vendor shall submit a comprehensive document detailing Acceptance Test procedures proposed under the contract to PUNJAB EDUSAT SOCIETY for its approval, within 10 days from the date of order. The random inspection of the installed equipment will be done by the Society with the help of Third Party. 

2.2.8 Vendor shall work out immediately after receiving order and in consultation with PUNJAB EDUSAT SOCIETY, an implementation plan detailing various milestones to the effect that all activities falling under the scope of the contract get completed within stipulated delivery schedule. 

2.2.9 The content of training and training material to be given to the participants should be clearly explained. Vendor to supply one hard copy of operating/technical manual with each unit of ROT. Vendor should also supply checkout documents for ROT, which will be approved by purchaser with changes, if any. 

2.2.10 Vendor shall work out, in consultation with PUNJAB EDUSAT SOCIETY, a detailed plan of preventive and corrective maintenance during and after the expiry of warranty period within one month on the placement of the separate CAMC order. Appropriate penalty clauses and other terms and conditions will be included in the plan. 

2.2.11 As a part of maintenance philosophy, Vendor to clearly focus on the following;

2.2.11.1 Fault reporting mechanism to be followed – by way of availability of number of maintenance/reporting centers, help desk etc. and by way of reporting by phone, fax e-mail etc. 

2.2.12
The successful bidder shall be responsible for transportation and installation of the terminals and other associated equipment at site. All the ordered ROTs will be transported, installed, commissioned and maintained by the vendor. During the warranty and/or CAMC period, vendor is fully responsible for all equipments supplied as part of this order. The remote terminals must work with normal domestic earthing. 
2.2.13        The remote nodes shall be so designed that they are easily installable in the field and pointed properly to the satellite with the help of set-top-box monitor/display of signal strength. The 40” or above LCD Large Format Display /Professional Display and Set Top Box must be kept aesthetically in the cabinet/stand to ensure protection from dust. The actual number of site locations will be given separately. The names of contact person at each place (with alternative 2nd name, if available) will be furnished in the due course. The general guidelines for wooden cabinet alongwith diagram for indoor equipments of ROT are given in Appendix.  
2.2.14 The Bidder shall submit the time schedule including supply, installation, commissioning and operationalization of the complete network. However, this period shall, in any case, not be more than 120 days from the issue of order or site readiness, whichever is later. LD clause, as mentioned in the tender document will be applicable, if the time schedule promised by the bidder is not adhered to. Vendor shall work out, within 15 working days of the placement of the order and in consultation with PUNJAB EDUSAT SOCIETY, an implementation plan detailing various milestones to the effect that all activities falling under the scope of the contract get completed within stipulated time.
Section - III

3.0 Installation of ROTs: 

3.1
Site Survey:

3.1.1
Vendor shall do the site survey for the sites for ROTs installation. Any non-suitability observed at site must be informed to user agency/respective nodal agency for corrective action. 

3.2 Foundation:
3.2.1
All civil works related to foundation of terminals, proper harnessing and weather proof flexible (ISI Marked) conduit pipe for routing RF cables at sites, etc. will be the responsibility of the vendor.

3.2.2 The Location for foundation is to be given by the respective Nodal Agency keeping in view the Line Of Sight Clearance. Legs of antenna stand should be grouted with cement (penetrating mount). Vendor has to make arrangement for foundation materials and labourers. 

3.2.3 The mount of the antenna should be sufficiently rugged to withstand wind velocity of 180 Km/hrs (survival). The Bidder shall submit the required analysis, in his technical bid, to substantiate the survival and operational wind velocity specifications. Please note that the bid will not be considered for further evaluation if it is not accompanied with such an analysis. 

3.3 Transportation:
3.3.1 Vendor shall cover transit insurance for value of the materials to be transported. This insurance policy shall cease once the equipments are safely handed over to the custodians of the respective classrooms. 

3.3.2 All the subsystems are to be transported safely with proper packing to each site with packing list containing all details of hardware packed with serial Nos. and quantity. 

3.3.3 Vendor shall prepare delivery schedule for distribution of subsystems in consultation with respective nodal agencies and also inform site coordinator well in advance. 

3.3.4 All additional taxes (Toll Tax, RTO Tax etc.) during transportation will be borne by the vendor. 
3.4 Installation  and  Deployment:

3.4.1 The Installation and commissioning should be carried out at sites as per the list given by the respective nodal agencies/PUNJAB EDUSAT SOCIETY and signature to be obtained in the form of ‘Hand Over and Acceptance Certificate’ from the users. 

3.4.2 Logistic support in respect of installation & deployment will be the responsibility of the vendor. 

3.4.3 During installation, satellite signal containing video pattern & audio tone will be transmitted by the Nodal Agency from Hub for subjective checkout of classroom. 

3.4.4 During installation of receive classrooms, if any of the sub system/component is found faulty, vendor shall replace/ repair and make the classroom operational. 

3.4.5 Channeling/dressing of RF/Interface cable is to be done by the vendor. 

3.4.6 Vendor shall provide detailed installation schedule and manpower deployed for the installation and commissioning and inform Nodal Agency. 

3.4.7 Vendor shall show functioning of ROT and get inspected the quality of workmanship to the concerned custodian/site in-charge and get it certified from the respective Nodal Agency. 
3.5 Acceptance Test: 

3.5.1 ROT acceptance test will be carried out by PUNJAB EDUSAT SOCIETY on at least one fully integrated terminal at the location decided/ provided by PES. 

3.5.2 The Test and Acceptance plan for the checkout of required classrooms should be prepared by the vendor and duly approved by the nodal agency/PUNJAB EDUSAT SOCIETY. Vendor has to carryout the test/checkout as per the test/acceptance plan. 

3.5.3 Test schedules must be planned in consultation with users/nodal agency.

3.5.4 During integrated test, user/nodal agency will provide satellite transmission with test signals as per the test schedule agreed mutually between vendor and user/nodal agency.

3.5.5 Vendor shall arrange test instruments required for carrying out integrated test & checkout of randomly selected few sites. 

3.5.6 Vendor shall prepare document containing test results of all terminals duly signed by user/nodal agency, which conducts and witnesses the test, and approved by the respective nodal agency official. 

3.5.7 It is a mandatory for the vendor to take photographs of foundation, quality of harnessing for all sites, before and after the completion of the work alongwith site witness, using digital camera. The photographs CDs/Floppies will be submitted to the respective nodal agencies/PUNJAB EDUSAT SOCIETY as a proof of the completion of the work satisfactorily. 
3.6 Maintenance Service:

3.6.1 Vendor for maintenance can be himself or vendor’s authorized Party. However, the vendor will be a single contact point, which carries out maintenance activities of complete respective network. 

3.6.2 All the items in the systems supplied against this order should be covered under on-site warranty for a period of one year after the installation, Commissioning and acceptance of all the ROTs of that supply order, against   bad   workmanship,   manufacturing   defects,   etc. However the warranty for (1) 40” or above LCD Large Format Display /Professional Display & (2) 1 KVA  Line Interactive UPS shall be for period of 3 Years) 

3.6.3 Vendor shall co-ordinate following activities with the respective Nodal Agencies: 

3.6.4 Information about nonfunctioning of classroom by setting of a help desk at nodal agency/ Punjab Edusat Society.

3.6.5 Vendor shall co-ordinate with the nodal agencies with intimation to PUNJAB EDUSAT SOCIETY for replacement/ repair of subsystems. 

3.6.6 Vendor shall maintain/update inventory of each terminal on regular basis during Preventive Maintenance (PM) cycle. 

3.6.7 Vendor shall maintain separate help desk for co-ordination with Nodal Agency. Help desk cannot be shared for any other applications. The help desk should have Telephone/Fax/E-mail id for registration of the complaints. The complaints will also be registered, in parallel, by the concerned colleges/ Schools on the website being designed by the nodal agency. Vendor shall also browse this website daily for noting these complaints. The complaints registered on the website will be treated as the authentic and valid complaints to vendor and he shall attend to them irrespective of whether the complaints are already registered or not with him through phone / mail. 

3.6.8 Vendor will provide the Monthly-feedback/service-report on these complaints to PUNJAB EDUSAT SOCIETY through E-mail/Fax. 

3.6.9 During maintenance activities, Vendor will coordinate with respective Nodal Agencies for obtaining transmission support from Hub during field visit. 

3.6.10 Vendor shall deploy dedicated technical manpower for executing maintenance activities. 

3.6.11 Vendor must have office /help desk at every Education Circle i.e Jalandhar, Patiala and Faridkot. This office must be manned for 12 hours to receive complaints and report back to Nodal Agency on day-to-day basis. 

3.6.12 The Service engineer of the vendor shall take complaints on daily basis and visit concerned site and repair the faults of what-so-ever nature. He should prepare service report and submit it to the respective Nodal Agencies and PUNJAB EDUSAT SOCIETY within 7 days time. 

3.6.13 If services are found not satisfactory during any time of the contract, PUNJAB EDUSAT SOCIETY will have all the right to terminate the contract for the remaining period. If SP is not able to repair 70% of the complaints in 7 days time, received in a month will be treated as unsatisfactory and PUNJAB EDUSAT SOCIETY can terminate contract by giving one months notice.

3.6.14 Vendor shall furnish all details as specified in PM data sheet (which will be decided by vendor and PUNJAB EDUSAT SOCIETY mutually after placement of the order) during preventive maintenance cycle for each site and sent it to respective Nodal Agencies and PUNJAB EDUSAT SOCIETY. 
3.7 Preventive Maintenance:

3.7.1 In order to reduce down time following activities are to be carried out as part of Preventive Maintenance (PM).

3.7.2 To carryout preventive maintenance once in a year for ROTs which are not being attended for any breakdown calls/complaint within six months, in coordination with site authority.

3.7.3 During Preventive Maintenance vendor shall follow the guidelines /procedure as recommended by the Original Equipment Manufacturer (OEM) of the equipment.

3.7.4 Vendor shall carryout routine cleaning as per recommendations of OEM which includes cleaning of Antenna, feed; mount assembly, STB, 1, UPS and related accessories. 

3.7.5 To align antenna if it has moves from marked position.

3.7.6 Vendor shall replace any damaged subsystem/ parts.

3.7.7 Vendor shall check that all the screws and fasteners are properly screwed.

3.7.8 Vendor shall replace/repair the faulty cable/cable connectors, harnesses, observed during PM cycle. 

3.7.9 Vendor shall carry out Maintenance of 1 KVA UPS along with battery bank. 

3.7.10 Vendor shall provide status report on parameters of the sub systems of the ROT. Any problem/deviations/degradations during PM to be reported and corrective actions to be carried out immediately.
3.8 LD Clause:
3.8.1 During warranty period the down time of the remote terminal (ROT) will be accounted only if the fault/defects are not repaired or replaced within 7 working days. If it exceeds 7 days, the SP has to pay the Rs.200/- for  each and every day delay from the day of fault reporting of respective ROT with maximum ceiling of Rs.5000/-

3.8.2 The LD clause, if included would clearly be applicable if the delays are on account of SP. In case delays are on account of user’s end or Force majeure, no LD clause will be applicable.
3.9 Operation Training: 

3.9.1 The operation & training document prepared by vendor should be approved by the respective nodal agencies/PUNJAB EDUSAT SOCIETY. The SP has to provide hands on training to operational persons at each site.

3.9.2 Vendor shall prepare an operation and maintenance manual in Hindi. Vendor shall provide hands on training (practical training) on operations and primary-level of the corrective & preventive maintenance to all trainees and also prepare DOs & DONTs in Hindi for smooth operation of system and circulate at all sites.

3.9.3 The Training schedule must be planned in consultation with the users/respective nodal agencies. 

3.10 Augmentation of the Network/Shifting of Sites (Optional) 

3.10.1 Vendor is required to shift the existing sites as and when required by PUNJAB EDUSAT SOCIETY on additional payment agreed upon. The tasks are to be carried out while augmentation of the network/ shifting of site. 
3.11 Other Terms and Conditions: 

3.11.1 The Supplier, once order is placed, has to complete the Supply, Installation, Commissioning and Operationalization of ROTs within delivery schedule of 120 days given above. In case the supplier fails to complete this work in PUNJAB EDUSAT SOCIETY specified period in the order or any extension thereof allowed by PUNJAB EDUSAT SOCIETY HQ, the department shall have the right to recover from the Supplier as Liquidated Damages (LD) a sum at the rate of 0.5 % (1/2 %) of the value of undelivered goods per week not exceeding the total cost of 10% of undelivered systems. 

3.11.2 After submission of quotation, if required vendor shall be asked to deploy 1 ROT at venue will be decided later for demonstration/evaluation of ROT system as per guidelines of Technical Evaluation Committee (TEC). [Note: Bidder has to submit Test Certificates/results  of ROT systems/equipments  including  1 KVA Line Interactive UPS  as per the RFP specifications while submitting the Technical bid]
3.11.3 After commissioning, the antenna will be fixed with some lock-nut arrangement/araldite to prevent its unintended movement. 

3.11.4 All cables will be routed through a flexible PVC/metal conduit, inside the building, to protect from rodents. 

3.11.5 The 40” or above LCD Large Format Display /Professional Display cabinet will be strengthened at backside to protect from rodents. 

3.11.6 All connector-ends will be weather-proof and will be appropriately strengthened and sealed with suitable compound. 

3.11.7 All audio-video cables will be strengthened to make it more rugged. 

3.11.8 Vendor shall submit acceptance test procedure and test results for ROTs for evaluation before installation added with the submission of one ROT to PUNJAB EDUSAT SOCIETY for evaluation before installation. 

3.11.9 Certification of terminal installation shall be done by: Custodian at site, respective Coordinator, vendor’s Representative and PUNJAB EDUSAT SOCIETY representative. 

3.11.10 All channels of the receivers shall be tuned to the same receiving frequency to avoid mishandling of the equipment at the user end. Vendor shall provide Factory Lock/a facility to Receiver Lock to avoid mistuning. 

3.11.11 The court of Chandigarh only shall have jurisdiction to deal with and decide any legal matter or dispute whatsoever arising out of this contract.

3.11.12  Expenditure related to all logistics and transportation for replacement of parts/ Sub-systems/components has to be borne by the vendor.

3.11.13 The Punjab Edusat Society reserves the right to distribute the quantity among bidders at the L1 price. 

3.11.14 PES shall not be responsible for any accidental injury, death or any untoward incidents caused to the workman deployed during installation, testing, commissioning and training etc. while executing the order.

Section – IV
4.0 Bidders Qualifications:
4.1        The bidder must be reputed company/firm with relevant experience to supply, installed, commission and Operationalization of Satellite Based tele education networks or with experience of supply, installation and commissioning of computer hardware, system software, networking, studio equipment and UPS etc. for educational purposes.
4.2 The bidder shall submit a proof including purchase order and certificate towards satisfactory completion of job and post installation services under the ageis of state/centre government. 
4.3 The bidder must be in existence for last five years. 
4.4 The bidder must be authorized distributor/dealer/ agent / service provider who must provide satisfactory service after sales. He should produce letters from third party to support the maintenance/ repair of subsystem/ parts supplied as and when required during warranty & CAMC period. 

4.5 The bidder should have experience of handling ROT projects under the aegis of ISRO or any State/Central Government. (Copy of the Purchase order/work order should be attached). 
4.6 The average annual turnover of lead bidder should be more than 10 crores in last 5 preceding years. Attach balance sheet to prove the same. The OEM must have minimum average per year turnover of Rs. 40.00 Crores (Rupees Fourty Crores) for  supply, installation, commissioning and Operationalization of Satellite Based tele education networks or supply, installation and commissioning of computer hardware, system software, networking, studio equipment and UPS etc. for educational purposes.

4.7 The bidder shall submit a proof including purchase order and certificate towards satisfactory completion of job and post installation services under the ageis of state/centre government 5 financial years ended with 31st March 2011 and supply a certificate from Chartered Accountant in this regard. The bidder  also have to submit copies of balance sheets /profit & loss accounts/ annual reports of last three financial years (upto 31-Mar-2011).
Section – V
5.0 Submission of Bids
5.1
The bid should be submitted to Project Director, Punjab Edusat Society, SCO.104-106, 2nd floor, Sector-34 Chandigarh not later than the last date of submission, in a sealed cover superscribe as “Bid for supply, installation, commissioning and operationalization of Satellite Based Receive Only Terminals(ROTs) Network for Punjab Edusat Project. 

5.2 The bidder or a person/persons duly authorized by the bidder shall affix the bid with his seal. All pages of the bid, where signature required is not mentioned, shall be initialed by the bidder with his seal, except un-amended, printed literature. 

5.3 The Bidder is expected to carefully examine all instructions, forms, terms and specifications in the Tender Document. Failure to furnish all information required in the Tender Document or submission of a bid not substantially responsive to the Tender Document in every respect will be at the Bidder's risk and may result in the rejection of the bid. 

5.4 Clarification regarding Tender Document: A prospective Bidder requiring any clarification of the Tender Document may contact the office of the Society personally. The Society will try to respond to the query there and then. However, submission of request for clarification will not entitle the Bidder for any extension of time in submission of the Tender Document. 
5.5 Amendments in the Tender Document:
5.5.1 At any time up to the last date for receipt of bids, the Punjab Edusat Society may, for any reason, whether at its own initiative or in response to a clarification requested by a prospective Bidder, modify the Tender Document by an amendment. 
5.5.2 The amendment will be notified by general advertisement or through letter or by FAX or Email to the prospective Bidder/Bidders who have received the Tender Documents and the same will be binding on them. 

5.5.3 In order to afford prospective Bidder/Bidders reasonable time, or otherwise for any other reason, in which to take the amendment into account in preparing their bids, the Punjab Edusat Society may, at its discretion, extend the last date for the receipt of Bids. 

Section - VI
6.0 Terms and Conditions of the Tender:
6.1
Payment Terms: 

6.1.1
60% of the Contract value shall be paid on delivery of ROTs materials in good condition on pro-rata basis. 

6.1.2
30% payment will be released on satisfactory installation and Commissioning of the entire infrastructure and network. 

6.1.3 Balance 10% payment will be released against Bank Guarantee of equal sum. The Bank Guarantee shall be issued by a nationalized/ scheduled bank on Rs. 100/- non- judicial stamp paper and would be valid during warranty period. 

6.1.4 The bills alongwith certificate of installation& commissioning duly signed by the in-charge of respective site/location shall be submitted to Project Director Punjab Edusat Society. 

6.1.5 All payments will be subjected to tax deduction at source as applicable at the prevailing tax rates. 

6.2 Performance Bank Guarantee (PBG) 

6.2.1
The successful bidder will have to deposit a performance bank guarantee for an amount equivalent to 10 % of the contract value within 7 days of the issuance of LOI/Order. The PBG would be valid for a period after 6 months post warranty, failing which the LOI/order shall be withdrawn at the discretion of the Society and the EMD of the bidder shall be forfeited.

6.3 Time Schedule:

6.3.1
The supply, installation commissioning and Operationalization of Satellite Based Receive Only Terminals (ROTs) Network shall be completed within 120 days of order/LOI upon successful bidder or sites readiness, whichever is later.

6.4 Warranty: 

6.4.1 All the systems/sub-systems/equipments/accessories supplied against this order shall carry warranty for a period of 12 (Twelve) months (except (1) UPS & (2) 40” or above LCD Large Format Display /Professional Display) comprehensive on-site from the date of installation and acceptance after commissioning.

6.4.2 UPS & 40” or above LCD Large Format Display /Professional Display shall carry warranty for 36 months comprehensive. During the period of warranty, if found that the system/equipment is not conforming to the description, specification, quality, workmanship, etc. Bidder shall replace/repair the same at its cost on site.

6.4.3 If any defect/malfunctioning of system is noticed during the warranty period, free replacement should be done immediately.

6.4.4 Warranty certificate for each system and for all the equipments supplied shall be provided along with the invoice. 

6.4.5 Software upgrades, if any, released during Warranty period shall be supplied free of cost. 

6.5 Penalty Clause for Late Delivery/Installation:

6.5.1 In case supplies are not made within the delivery date stipulated at Sr. No. 2.2.14 or any extension thereof, LD @ 0.5% (zero point five percent) of the order value or part thereof of the undelivered portion for each calendar week of delay shall be recovered from the bills. However, the total Liquidated Damages shall not exceed 10% (ten percent) of the total value of each order. 

6.5.2 The penalty will be calculated on weekly basis. In case the delay exceeds one month, the order/contract will be liable to be cancelled along with forfeiture of bank guarantee and recovery of liquidated damages. 

6.5.3 The above provision is notwithstanding the right of the Punjab Edusat Society to get the work executed at the risk and cost of the Bidder and to avail of other remedies/provisions laid down in the terms of bid/contract. 

6.5.4 Termination for Default:

6.5.4.1 The Punjab Edusat Society may, without prejudice, to any other remedy for breach of contract, by 15 days written notice of default sent to the Bidder and the Bidder fails to cure the defect within the notice period, terminate the contract in whole or in part of it. The Punjab Edusat Society shall make payment for the system(s) duly supplied and/or service(s) performed including the work in progress, up to the date of termination.  The term “work in progress” shall include but not limited to the value of systems meant for delivery to the Punjab Edusat Society (i) for which manufacturing process was initiated by the Bidder; or (ii) order was placed by the Bidder on its vendors, prior to the date of termination.

6.5.4.2 The qualified Bidder fails to deliver any or all of the obligations within the time period (s) specified in the contract, or any extension thereof granted by the Punjab Edusat Society.

6.5.4.3 The qualified Bidder fails to perform any of the obligation(s) under the contract. 
6.5.4.4 The qualified Bidder becomes bankrupt or otherwise insolvent, provided that such termination will not prejudice or effect any right of action or remedy which has accrued to the Punjab Edusat Society.
6.6 Force Majeure: 

6.6.1 Notwithstanding the provisions of the tender, the Bidder shall not be liable for forfeiture of its performance security, liquidated damages or termination for default, if and to the extent that, its delay in performance or failure to perform its obligations under the contract is the result of an event of Force Majeure. 

6.6.2 For the purposes of this Clause, ‘Force Majeure' means an event beyond the control of the Bidder like acts of the Government of Punjab/ Punjab Edusat Society either in its sovereign or contractual capacity, war or revolution, fire, any natural calamity, floods, epidemics, quarantine restrictions and freight embargoes. 

6.6.3 If a Force Majeure situation arises, the qualified Bidder shall promptly notify the Punjab Edusat Society in writing of such a condition and the cause thereof. Unless otherwise directed by the Punjab Edusat Society in writing, the Bidder shall continue to perform its obligations under the contract as far as reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. The Punjab Edusat Society may terminate this contract, by giving a written notice of minimum 15 working days to the Bidder, if as a result of Force Majeure, the Bidder is unable to perform a material portion of the services for a period of more than 30 days.
6.7 Standard of Performance:

6.7.1 The qualified Bidder shall carry out the services and carry out its obligations under the contract with due diligence, efficiency and economy in accordance with generally accepted norms techniques and practices used in the industry. The Bidder/bidders shall also adhere to professional standards recognized by international professional bodies. The Bidder/bidders shall employ appropriate advance technology and safe and effective equipment, machinery, material and methods. The Bidder/Bidders shall always act in respect of any matter relating to this contract, as faithful advisors to the Society and shall, at all times support and safeguard the Society’s legitimate interests in any dealings with the third party.

6.8  Comprehensive Annual Maintenance Contract(CAMC): 

6.8.1 The bidder must quote separately for Comprehensive Annual Maintenance Contract (CAMC) of the equipment of ROTs offered onsite services. The duration of CAMC will be for 2 years after warranty period. This will commence immediately after satisfactory discharge of services under warranty.

6.8.2 The CAMC includes maintenance services, repair or replacement for all breaks down calls as reported by telephone, fax & e-mail. Vendor must confirm complain/docket number to users and maintain the log book and should attend complain within 3 working days. 

6.8.3 The term CAMC means vendor will diagnose, repair/replace the faulty components/subsystems/peripherals/software installed at all sites using its own resources with in the given time frame.
6.8.4 Payment: Payment will be made on quarterly basis at end of each quarter after submission of quarterly reports duly certified by site In-Charge/Coordinator for satisfactory performance for each activity on Pro-rata basis.

6.8.5 Under CAMC of ROT, vendor shall be carrying out activities like reconfiguration of ROT with new parameters and reorientation of antenna during change over from one satellite to other satellite if required. (Optional) 
6.8.6 Other Terms and Conditions: 

6.8.6.1 Fall Clause: The prices charged for the stores supplied under contract by the contractor shall in no way exceed the lowest price at which the contractor sells the stores or offer to sell stores of identical description on similar terms and conditions to any person/Organization including the purchaser or any department of the Central Govt. or any Dept. of the State Govt. or any statutory undertaking of the Central or State Govt. as the case may be during the period till performance of the supply order placed during the currency of the contract is completed. 
6.8.6.2 If at any time during the said period the contractor reduces the rate of sale price, sells or offers to sell such stores to any person/Organization including the purchaser or any Dept. of Central Govt. or any Dept. of State Govt. or any statutory undertaking of the central or State Govt. as the case may be at price lower than the price chargeable under the contract shall forthwith notify such reduction sale or offer to sell to the Society and the price payable under the contract for the stores supplied after the date of coming into force of such reduction or shall offer to sell shall stand correspondingly reduced. 
6.8.6.3 The contractor shall furnish the following certificate alongwith each bill or payment for supplies made against the contract. The supplier has to certify that there has been no reduction in sale price of the stores of description identical to the stores supplied to the Govt. under the contract herein and such stores have not been offered and sold by him on similar terms and conditions to any person/Organization including the purchaser of any Dept. of the Central Govt. or any Dept. of the State Govt. or any statutory undertaking of the Central or State Govt. as the case may be upto the date of the bill/date of completion of supplies against the supply order placed during the currency of the contract at a price lower than the price charged to the Society under the contract. 
6.8.6.4 The Punjab Edusat Society reserves the right to carry out the capability assessment of the Bidder. The Society’s decision shall be final in this regard. 
6.8.6.5 The Punjab Edusat Society reserves the right to accept or reject any/all tenders without assigning any reason. 
6.8.6.6 The Punjab Edusat Society reserves the right to increase or decrease the quantities of items to be purchased or drop any item all together. 

6.9 Arbitration: 

6.9.1 All disputes, differences, claims and demands arising under or pursuant to or touching the contract shall be referred to the sole arbitrator i.e. the Principal Secretary/Secretary to Government of Punjab, Department of Secondary Education. This is notwithstanding the fact that the sole arbitrator may be connected in any manner with the official process of finalizing the Contract. The award of the sole arbitrator shall be final and binding on both the parties under the provisions of the Arbitration and Conciliation Act, 1996 or by statutory modification re-enactment thereof for the time being in force. Such arbitration shall be held at Chandigarh. 
6.10 Jurisdiction: 

6.10.1
In all matters and disputes arising hereunder the appropriate Courts at Mohali alone shall have jurisdiction to entertain and try them. 
Annexure – I

Specification of the Receive Only Terminal (ROT) System:

1.  Antenna system

	Sr. No.
	Description  
	Specification 
	Specification of the items offered by the bidder
	Make/ Model No.
	Page No of Document containing specifications
	Deviation, if any from the prescribed specification with justification

	1
	Rx frequency
	Ku-band 

10.7 to 12.7 GHz
	
	
	
	

	2
	Aperture
	0.9 Mtr.
	
	
	
	

	3
	Dish type
	Single Reflector 
	
	
	
	

	4
	Reflector Optics
	Offset focus
	
	
	
	

	5
	Cross Polar isolation
	> 30 dB (on axis)
	
	
	
	

	6
	Gain (Typical)
	>38dB @11.85GHz
	
	
	
	

	7
	F/D ratio
	0.5
	
	
	
	

	8
	El Movement

	10-900
	
	
	
	

	9
	Az Movement
	+/- 1800
	
	
	
	

	10
	G/T@ 500 EI
	> 18.0 db / 0 K
	
	
	
	

	11
	Wind loading capacity:

Wind (Operational)

Wind (Survival)
	100 Km/Hour

180 Km/Hour
	
	
	
	

	12
	Operating temperature 
	-100 to +500 C
	
	
	
	

	13
	Mount
	Az / EL type

Penetrating 

(heavy duty)
	
	
	
	

	14
	Polarization 
	Linear Horizontal/Vertical 
	
	
	
	


Note: 

1. Vendor shall provide make, model and detailed specifications of antenna system like reflector type, optics, material, mount type & material etc. in the technical bid.

2. Vendor shall compute G/T and provide the break-up of the G/T including total noise temp of the system, in the technical bid.

3. Vendor shall provide wind load certification to confirm the wind loading capacity of 0.9m with Penetrating Mount.

4.  Vendor shall provide foundation drawing.
2. LNBF (Ku Band Universal)

	Sr. No.
	Description
	Specification
	Specification of the items quoted by the bidder
	Make/ Model No.
	Page No of Document containing specifications
	Deviation, if any from the prescribed specification with justification

	1
	I/P Freq Range
	Low Band :

10.70-11.7 GHz

High Band :

11.7-12.75GHz
	
	
	
	

	2
	O/P Frequency Range
	Low Band: 

950-1950 MHz

High Band:

1100-2150 MHz
	
	
	
	

	3
	Output connector type
	75 ohms Female F - Connector
	
	
	
	

	4
	Input feed horn type
	Linear, Optimize for Offset dish

F/D ratio from 0.45 to 0.70
	
	
	
	

	5
	Noise Figure
	0.5 dB, Typical 
	
	
	
	

	6
	(Note: The vendor should choose the LNB noise figure such that the G/T specification of the respective ROT is met)
	
	
	
	

	7
	LO
	Low Band: 9.750GHz

High Band:10.60GHz
	
	
	
	

	8
	LO stability 
	+/- 3 MHz or better
	
	
	
	

	9
	LO Phase noise @ 1 KHz
	-65 dBc/Hz, Typical
	
	
	
	

	10
	LO Phase noise @ 10 KHz
	-80 dBc/Hz, Typical
	
	
	
	

	11
	LO Phase noise @ 100 KHz
	-100 dBc/Hz, Typical
	
	
	
	

	12
	Conversion Gain
	55 dB, Typical
	
	
	
	

	13
	Cross Polarization 
	25dB (Minimum) 
	
	
	
	

	14
	Gain Variation
	5 dB pk-pk/36 MHz (Over full band)
	
	
	
	

	15
	Image Rejection
	40 dB, Min
	
	
	
	

	16
	Impedance 
	Output: 75 ohm
	
	
	
	

	17
	I/P & O/P VSWR
	2.5:1 (Max) 
	
	
	
	

	18
	DC Operating Voltage  
	14.0 V to 18.0 V 
	
	
	
	

	19
	Temperature 
	Operating: -10 0 C to +500 C 

Storage: -10 to0 C +600 C 
	
	
	
	

	20
	Relative Humidity
	95% non-condensing at 40 0 C
	
	
	
	


3. Digital Set Top Box (DVB-S Satellite Receiver)

	Sr. No.
	Description
	Specification
	Specification of the items quoted by the bidder
	Make/ Model No.
	Page No of Document containing specifications
	Deviation, if any from the prescribed specification with justification

	1
	Input Frequency Range
	950-2150 MHz
	
	
	
	

	2
	I/P level
	-25 to –65 dBm (nominal level -45 dBm)
	
	
	
	

	3
	Channel selection
	PLL synthesizer
	
	
	
	

	4
	System
	MPEG-2, fully DVB-S Compliant
	
	
	
	

	5
	Modulation
	QPSK
	
	
	
	

	6
	I/P Impedance
	75 Ohm
	
	
	
	

	7
	Connector (I/P)
	75 Ohm female F-Connector 
	
	
	
	

	8
	Symbol Rate
	1 MSPS to 45 MSPS
	
	
	
	

	9
	Video decoder
	MPEG-2
	
	
	
	

	10
	Video Format
	4:3, 16:9
	
	
	
	

	11
	Video Transfer Rate

	15 Mbps
	
	
	
	

	12
	TS Data Rate
	60 Mbps
	
	
	
	

	13
	Return Loss
	8 to 10 dB
	
	
	
	

	14
	Video Resolution
	720 x 576 PAL
	
	
	
	

	15
	Audio Decoder
	MPEG-1, MPEG-2, MPEG-Layer3
	
	
	
	

	16
	Audio Mode
	Mono, Stereo
	
	
	
	

	17
	Sampling Rate
	32, 44.1, 48 KHz
	
	
	
	

	18
	Memory
	
	
	
	
	

	18a
	FLASH
	16 Mb (2 Mbyte) or better
	
	
	
	

	18b
	SDRAM
	64 Mb (8 Mbyte) or better
	
	
	
	

	19
	Data port
	RS 232 (DB9 female) 
	
	
	
	

	20
	A/V Output
	Video: 1xRCA, Audio: 2xRCA
	
	
	
	

	21
	Remote control operation
	Required
	
	
	
	

	22
	Password protection 
	Required
	
	
	
	

	23
	DC output (For LNBC drive)
	14V to 18V
	
	
	
	

	24
	Voltage control for change of polarization 


	Required 
	
	
	
	

	25
	Power Supply
	
	
	
	
	

	25a
	I/P Voltage
	90-270V AC, 50 Hz +/- 5%
	
	
	
	


	Sr. No.
	Description
	Specification
	Specification of the items quoted by the bidder
	Make/ Model No.
	Page No of Document containing specifications
	Deviation, if any from the prescribed specification with justification

	26
	Power Consumption
	<20 W
	
	
	
	

	27
	RF Modulator
	PAL-B 
	
	
	
	

	28
	RF O/P Channel
	VHF/UHF Channel 
	
	
	
	

	29
	RF O/P Level
	60 dBu V to 80 dBu V
	
	
	
	

	30
	Various channel editing functions (favorite, add delete and parental lock)
	Required
	
	
	
	

	31
	SCPC and MCPC received from Ku – Band satellite 
	Required
	
	
	
	

	32
	Physical
	
	
	
	
	

	32a
	Operating Temperature
	0-450 C
	
	
	
	

	32b
	Humidity
	95% non condensing at +400 C
	
	
	
	


Note: 
Vendor shall quote for STB with USB port, for recording of program on USB Pen derive or USB hard disk as option. (Keeping the above specifications for STB) 

4. IFL Cable

	Sr. No.
	Description
	Specification
	Specification of the items quoted by the bidder
	Make/ Model No.
	Page No of Document containing specifications
	Deviation, if any from the prescribed specification with justification

	1
	Cable type 
	RG 6 

(Centre conductor should be pure copper  material) 

(Jelly filled cable preferred) 
	
	
	
	

	2
	Length
	30 mtr
	
	
	
	

	3
	Input & output impedance
	75 ohm
	
	
	
	

	4
	Type of connector (I/O)
	F connector (Male at both ends)

(Professional grade Connectors required) 
	
	
	
	

	5
	Loss (for 25 meter length of cable) 

At 950 MHz 

At 2150 MHz 
	Around  7 dB

Around 10 dB
	
	
	
	


5.    40” or above LCD Large Format Display /Professional Display (With Wall Mounted Kit)
	Sr. No.
	Description
	Specification
	Specification of the items quoted by the bidder
	Make/ Model No.
	Page No of Document containing specifications
	Deviation, if any from the prescribed specification with justification

	1
	Screen Size
	40"+above 
	
	
	
	

	2
	Aspect Ratio
	16 : 9  &  4:3 (Switchable) 
	
	
	
	

	3
	Native Resolution
	1920 x 1080 (Full HD)
	
	
	
	

	4
	Brightness
	450cd/m2 or above
	
	
	
	

	5
	Contrast Ratio
Dynamic

Native 
	40,000:1 
 3,000:1
	
	
	
	

	6
	Viewing Angle
(H x V)
	> 170 x 170
	
	
	
	

	7
	Response Time
	2 to 8 ms
	
	
	
	

	8
	Surface Treatment
	Anti Reflection 
	
	
	
	

	9
	Life time
	≥ 50,000 Hours
	
	
	
	

	10
	VIDEO(PC)
	 
	
	
	
	

	10a
	Input Resolution
	Should support 1920 X 1080 and lower resolutions 
	
	
	
	

	10b
	H-Scanning Frequency
	30 ~ 83kHz 
	
	
	
	

	10c
	V-Scanning Frequency
	56 ~ 85 Hz 
	
	
	
	

	10d
	Sync Compatibility
	Separate, Composite, Digital
	
	
	
	

	10e
	PC Video Input
	RGB, HDMI & DVI
	
	
	
	

	11
	INPUTS
	 
	
	
	
	

	11a
	Composite Video
	Required
	
	
	
	

	11b
	PC via 15-Pin Sub "D"
	Required
	
	
	
	

	12
	Input/Output
	 
	
	
	
	

	12a
	Composite Video Input
	Required 
	
	
	
	

	12b
	Audio Output
	Required
	
	
	
	

	12c
	Audio Inputs
	Required
	
	
	
	

	12d
	HDTV Formats
	Required
	
	
	
	

	12e
	HDMI & DVI with HDCP
	Required
	
	
	
	

	12f
	RS-232C (In/Out) 
	Required 
	
	
	
	

	12g
	RJ-45
	Required
	
	
	
	


	Sr. No.
	Description
	Specification
	Specification of the items quoted by the bidder
	Make/ Model No.
	Page No of Document containing specifications
	Deviation, if any from the prescribed specification with justification

	13
	AUDIO
	 
	
	
	
	

	13a
	Auto Volume 
	Required
	
	
	
	

	13b
	Balance
	Required
	
	
	
	

	13c
	Audio Power
	20W (10W x 2)
	
	
	
	

	13d
	Speaker On/off
	Required
	
	
	
	

	13e
	 Speakers 
	Required (Built in)
	
	
	
	

	14
	Features
	
	
	
	
	

	14a
	Source Selection
	HDMI & DVI, RGB,   AV
	
	
	
	

	14b
	Energy Saving
	Required 
	
	
	
	

	14c
	Wall mount

	with wall mounting Kit
	
	
	
	

	15
	POWER
	
	
	
	
	

	15a 
	Power Supply
	100-240V~ AC,  50/60Hz
	
	
	
	

	15b
	Power Type
	Built-in Power
	
	
	
	

	15c
	Power Switch 
	Required
	
	
	
	

	15d
	Power Consumption
	 
	
	
	
	

	
	 Normal
	max 235W
	
	
	
	

	
	Power Off (Standby)
	< 1W
	
	
	
	

	16
	STANDARD CERTIFICATION Required like:
	
	
	
	

	16a
	Safety
	UL / cUL / CB scheme / TUV
	
	
	
	

	16b
	EMC
	FCC Class "B" 
	
	
	
	

	16c
	Energy Star 5.0
	Required as per Energy star website 
	
	
	
	


6   1 KVA Line Interactive UPS
	Sr.    No.
	Description
	Specifications 
	Specification of the items quoted by the bidder
	Make/ Model No.
	Page No of Document containing specifications
	Deviation, if any from the prescribed specification with justification

	1
	Ups Capacity in KVA
	1 KVA
	
	
	
	

	1.1
	 Topology
	Line Interactive
	
	
	
	

	1.2
	Make /Model
	To be given by Bidder
	
	
	
	

	2
	Input
	
	
	
	
	

	2.1
	Nominal input voltage
	230V (Single Phase)
	
	
	
	

	2.2
	Input Frequency
	50HZ +/- 3Hz
	
	
	
	

	2.3
	Input Connection Type
	IEC – 320 C14
	
	
	
	

	2.4
	Input voltage range for mains operations.
	160 – 285V
	
	
	
	

	2.5
	Input Voltage adjustable range for mains operations.
	151 – 302V
	
	
	
	

	3
	Output
	
	
	
	
	

	3.1
	Output Power Capacity (VA)
	1000VA
	
	
	
	

	3.2
	Power Factor 
	0.8
	
	
	
	

	3.3
	Output power capacity (W)
	800W
	
	
	
	

	3.4
	Nominal output voltage
	230V  (Single Phase)
	
	
	
	

	3.5
	Output Voltage Distortion
	Less than +/- 5% at full load 
	
	
	
	

	3.6
	Output frequency
	47 – 53 Hz
	
	
	
	

	3.7
	Crest Factor
	3:1
	
	
	
	

	3.8
	Waveform type
	Sine wave
	
	
	
	

	3.9
	Output Connections 
	8 Numbers of IEC320 and 2 Numbers of IEC Jumpers
	
	
	
	

	4
	Batteries
	
	
	
	
	

	4.1
	Battery type
	Sealed Maintenance free
	
	
	
	

	4.2
	Battery Make/Model No
	Exide/Amar Raja/Panasonic/Rocket/ OKAYA/LUMINOUS 
	
	
	
	

	4.3
	Backup time
	Minimum 4 Hrs back up (On full load of ROT including 40” or above LCD Large Format Display /Professional Display)
	
	
	
	


	Sr.    No.
	Description
	Specifications 
	Specification of the items quoted by the bidder
	Make/ Model No.
	Page No of Document containing specifications
	Deviation, if any from the prescribed specification with justification

	4.4
	AH Rating of individual Batteries
	100AH.
	
	
	
	

	4.5
	Number of 100 AH Batteries required for minimum 4 hours back up (On full load of ROT including 40” or above LCD Large Format Display /Professional Display)
	To be given by bidder
	
	
	
	

	4.6
	Battery Charging
	Temperature compensated battery charging
	
	
	
	

	4.7
	Battery Charging time
	6 to 8 Hours
	
	
	
	

	4.8
	Charger Capacity
	Minimum 15 A
	
	
	
	

	4.9
	Battery transfer time
	4 ms or better 
	
	
	
	

	5
	Communications & Management 
	
	
	
	
	

	5.1
	Interface port
	RS232
	
	
	
	

	5.2
	Inverter Efficiency
	90%
	
	
	
	

	5.3
	Overall Efficiency
	90%
	
	
	
	

	5.4
	Automatic restart of load
	Required
	
	
	
	

	5.5
	Cold start capability
	Required
	
	
	
	

	5.6
	Generator compatibility
	To provide clean uninterrupted power when Generator is used
	
	
	
	

	5.7
	LED display
	A) Online
B) On Battery
C) Replace battery
D) Overload
	
	
	
	

	5.8
	Alarms
	A) On battery
B) Low battery
	
	
	
	

	5.9
	Operating Temperature
	0 to 40 deg C
	
	
	
	

	5.10
	Relative Humidity
	0-95% Non condensing at 40 deg C
	
	
	
	

	5.11
	Noise level
	Less than 45dBA
	
	
	
	

	5.12
	Approvals
	CE, EN50091-1, EN50091-2
	
	
	
	


	Sr.    No.
	Description
	Specifications 
	Specification of the items quoted by the bidder
	Make/ Model No.
	Page No of Document containing specifications
	Deviation, if any from the prescribed specification with justification

	6
	Protections
	
	
	
	
	

	6.1
	Surge protection
	As per IEC 61000-4-5 Class 3 & as per IEC 61000-4-5 (Protection against, up to 2KVA surges)
	
	
	
	

	6.2
	Sustained input over voltage protection
	Required
	
	
	
	

	6.3
	Sustained Short circuit protection
	Required
	
	
	
	

	6.4
	Full time EMI/RFI suppression
	Required
	
	
	
	

	7
	External Extension  Electric board ( 2 Mtr Wire)
	Three Number 5 pin sockets required with mains indicator.
	
	
	
	


Notes: 

1. Vendor shall decide the capacity of battery and number of batteries to meet the requirement of 4 hrs back up time considering the total load (Watt) consumed by all ROT sub-systems including 40” or above LCD Large Format Display /Professional Display. 

2. Vendor shall submit calculations of (1) Number of batteries & (2) VA to be provided, based on the total load (Watt) consumed by all ROT sub-systems including 40” or above LCD Large Format Display /Professional Display. (considering 4 hours backup time) 

Annexure – II

Format for submitting the Commercial bid

The vendor will submit the quote strictly in the format given below:

	Sr.

No.
	Items
	Make & Model 
(to be provided compulsorily)
	Cost Per Unit

	1
	0.9m      Ku-band      antenna  with Penetrating Mount and  feed (powder coated for outside weather)
	
	

	2
	 Ku-band      LNBF
	
	

	3
	Digital Set Top Box with remote control for DVB-S
	
	

	3a
	Digital Set Top Box with remote control for DVB-S with USB Facility(Optional)
	
	

	4
	40” or above LCD Large Format Display /Professional Display with remote   control with wall mounted accessories 
	
	

	5
	Wall mounted wooden   cabinet   for Indoor equipment of ROT like (1) STB, (2) 40” or above LCD Large Format Display /Professional Display, etc.
	
	

	6
	 1KVA Line Interactive UPS with Batteries)
	
	

	7
	IFL Cable ( RG-6, 30m)
	
	

	Services
	
	

	8
	Installation and Commissioning 
	
	

	9
	The comprehensive AMC for 2 years after one year free warranty over (CAMC to be quoted in terms of the percentage of the material cost excluding the cost of the services) Except UPS and 40” or above LCD Large Format Display /Professional Display
	
	

	10
	Un-installation and Reinstallation of the ROTs at other site (Shifting of the site), if required 
	
	

	11
	Transport Charges of all equipments per site
	
	

	12
	Others, if any  
	
	


Note:- The Quantity is approximate and can vary

Annexure-III
List of Deliverables

	Sr. No
	Items
	Quantity 

	1
	0.9 M Ku-Band antenna with Penetrating Mount and  feed (powder coated for outside weather)
	2790

	2
	Ku-Band LNBF
	2790

	3
	Digital Set Top Box with remote control for DVB-S
	2790

	3a
	Digital Set Top Box with remote control for DVB-S with USB Facility(Optional)
	

	4
	40” or above LCD Large Format Display /Professional Display  with remote   control with wall mounted accessories
	2790

	5
	Wall mounted wooden   cabinet   for Indoor equipment of ROT like (1) STB, (2) 40” or above LCD Large Format Display /Professional Display, etc.
	2790

	6
	1KVA Line Interactive UPS with Batteries)
	2790

	7
	IFL Cable ( RG-6, 30m)
	2790


Appendix 

General Guidelines for Wooden cabinet for indoor equipments of ROT 

	Sr. No
	Guidelines

	1
	Wall mount wooden Cabinet with floor-stand  ,having   provision to mount all indoor items of ROT like STB, 40” or above LCD  LFD/ Professional Display, Etc, (Line Interactive UPS will be kept on floor ) 

	2
	Should be made of high quality  ISI grade pre-laminated board with edge banded  PVC beading

	3
	Should have modular knockdown construction for easy transportation and assembly at  site

	4
	Should have suitable partitioning box for Set Top Box, 40” or above LCD LFD/ Professional Display 

	5
	Should have ventilation for heat dissipation generated ROT equipments. 

Ventilation at sides using perforated plastic grill  for air circulation to be provided

	6
	40” or above LCD  LFD / Professional Display Partition to be fitted with double doors multifold  type so that they do not project outside in open condition

	7
	Wall mount Cabinet should equipped with two supports lags to  withstand load of all indoor equipments 

	8
	Should have easy opening of front door & locking arrangement.

Should have master key, which can be used to open locks of all the supplied cabinets.

	9
	Should have two standard cable-manager holes of about 3”dia to be provided.

	10
	Should have dust free & Protection from access to rodents, rats, etc. 



	11
	Bidder shall submit detailed drawing along with photograph of the proposed wooden cabinet in technical proposal.


[image: image1.jpg]



[image: image2.jpg]



[image: image3.jpg]



[image: image4.jpg]


[image: image5.jpg]



Page 33 of 35

